## Sheet1
Serial No | Project Name | Submittal Name | Document Name | Document Type | Current Status | Next Level Action | ONTB Reference # | Originator Reference # | Incoming Recv. Date | Flow Name |  |  |  | Accepted/Rejected Date | Remarks
1 | CP-27 | Regarding Resubmission of Backup documents for RA bill-04. | 184(A).Letter for Submission of supporting documents for RA Bill | PDF | Submitted |  | KBR/BWSSB/CP-27/Supporting Documents/184(A)/2022-2 | KBR/BWSSB/CP-27/Supporting Documents/184(A)/2022-23 | 2022-11-08 | Flow 1 | Download | No History | View Details | N/A
2 | CP-27 | Regarding Inspection of DWC pipes-M/s Kiran Infratech | 380.Letter for Inspection of DWC Pipes -Kiran Infratech | PDF | Submitted |  | KBR/BWSSB/CP-27/DWC Pipes/Inspection/380/2022-23 | KBR/BWSSB/CP-27/DWC Pipes/Inspection/380/2022-23 | 2022-11-08 | Flow 1 | Download | No History | View Details | N/A
3 | CP-27 | Regarding 8th Monthly Environmental Monitoring report | 8th Monthly EMoP report for July 2022- Final | PDF | Submitted |  | KBR/BWSSB/CP-27/8th EMoP/July/382/2022-23 | KBR/BWSSB/CP-27/8th EMoP/July/382/2022-23 | 2022-11-08 | Flow 1 | Download | No History | View Details | N/A
5 | CP-27 | Regarding slow or no progress at site | 313.Letter regarding Slow or no progress of work 4 MLD STP | PDF | Submitted |  | KBR/BWSSB/CP-27/4 MLD STP/313/2022-23 | KBR/BWSSB/CP-27/4 MLD STP/313/2022-23 | 2022-11-08 | Flow 1 | Download | No History | View Details | N/A
6 | CP-27 | Regarding Release the payment for MIS Implementation | 379.Letter for release the payment for MIS Implementation | PDF | Submitted |  | KBR/BWSSB/CP-27/MIS/Payment request/379/2022-23 | KBR/BWSSB/CP-27/MIS/Payment request/379/2022-23 | 2022-11-08 | Flow 1 | Download | No History | View Details | N/A
7 | CP-27 | RCC Pipe Inspection M/s. Kalva Spun concrete pipes | 381.Letter for Inspection of RCC pipes-Kalva Spun pipes | PDF | Submitted |  | KBR/BWSSB/CP-27/RCC Pipes/Inspection/381/2022-23 | KBR/BWSSB/CP-27/RCC Pipes/Inspection/381/2022-23 | 2022-11-08 | Flow 1 | Download | No History | View Details | N/A
8 | CP-27 | Di pipe Inspection-Revised | 309.Letter for Inspection of DI pipes | PDF | Submitted |  | KBR/BWSSB/CP-27/DI pipe/Inspection/309/2022-23 | KBR/BWSSB/CP-27/DI pipe/Inspection/309/2022-23 | 2022-10-08 | Flow 1 | Download | No History | View Details | N/A
9 | CP-27 | Monthly report-June 2022 | Monthly report-June 2022 | PDF | Submitted |  | KBR/BWSSB/CP-27/MPR-June/279/2022-23 | KBR/BWSSB/CP-27/MPR-June/279/2022-23 | 2022-10-08 | Flow 1 | Download | No History | View Details | N/A
10 | CP-27 | Request for DWC pipe Inspection-Kiran Infratech Ltd | 246.Letter regarding DWC Pipes of Ms. Kiran Infratech | PDF | Submitted |  | KBR/BWSSB/CP-27/DWC Pipes/Inspection/246/2022-23 | KBR/BWSSB/CP-27/DWC Pipes/Inspection/246/2022-23 | 2022-10-08 | Flow 1 | Download | No History | View Details | N/A
11 | CP-27 | Regrading Fencing of 9 MLS Nagasandra STP | 310.Letter regarding fencing of 9 MLD STP at Nagasandra | PDF | Submitted |  | KBR/BWSSB/CP-27/9 MLD/Compliance/310/2022-23 | KBR/BWSSB/CP-27/9 MLD/Compliance/310/2022-23 | 2022-10-08 | Flow 1 | Download | No History | View Details | N/A
13 | CP-27 | Regrading to Lay PCC at Hemigepura Aeration basin | 336.Letter for Pouring of PCC for Aeration basin at Hemigepura STP | PDF | Submitted |  | KBR/BWSSB/CP-27/Aeration basin PCC laying/336/2022 | KBR/BWSSB/CP-27/Aeration basin PCC laying/336/2022-23 | 2022-10-08 | Flow 1 | Download | No History | View Details | N/A
17 | CP-27 | Reimbursement of increase in GST rate | 362.Regarding increase in GST rate | PDF | Submitted |  | KBR-AIPPL-JV/BWSSB/CP-27/GST/2022-23/362 | KBR-AIPPL-JV/BWSSB/CP-27/GST/2022-23/362 | 2022-08-08 | Flow 1 | Download | No History | View Details | N/A
24 | CP-27 | Regarding furnishing of Computer with Printer to client site office-RR Nagar Zone | 337.Letter for handing over of system & printer-WWM-110V | PDF | Submitted |  | KBR/BWSSB/CP-27/Handing over of PC & printer/337/2 | KBR/BWSSB/CP-27/Handing over of PC & printer/337/2022-23 | 2022-05-08 | Flow 1 | Download | No History | View Details | N/A
25 | CP-27 | Regarding furnishing of Computer with Printer to client site office-Dasarahalli zone | 338.Letter for handing over of system & printer-Cst | PDF | Submitted |  | KBR/BWSSB/CP-27/Handing over of PC & printer/338/2 | KBR/BWSSB/CP-27/Handing over of PC & printer/338/2022-23 | 2022-05-08 | Flow 1 | Download | No History | View Details | N/A
26 | CP-27 | Ambulance tie up at Dasarahalli zone | 341.Ambulance tieup-Dasarahalli zone | PDF | Submitted |  | KBR/BWSSB/CP-27/Ambulance tie up/341/2022-23 | KBR/BWSSB/CP-27/Ambulance tie up/341/2022-23 | 2022-05-08 | Flow 1 | Download | No History | View Details | N/A
27 | CP-27 | Ambulance tie up-RR nagar | 342.Ambulance tieup-RR Nagar Zone | PDF | Submitted |  | KBR/BWSSB/CP-27/Ambulance tie up/342/2022-23 | KBR/BWSSB/CP-27/Ambulance tie up/342/2022-23 | 2022-05-08 | Flow 1 | Download | No History | View Details | N/A
30 | CP-27 | 2nd Quarterly Environmental Monitoring report | 2nd Quarterly EMop report | PDF | Submitted |  | KBR/BWSSB/CP-27/2nd Quarterly EMoP/333/2022-23 | KBR/BWSSB/CP-27/2nd Quarterly EMoP/333/2022-23 | 2022-01-08 | Flow 1 | Download | No History | View Details | N/A
42 | CP-27 | DI Specials Inspection | 316.Letter for Inspection of DI Specials | PDF | Submitted |  | KBR/BWSSB/CP-27/DI Specials/Inspection/316/2022-23 | KBR/BWSSB/CP-27/DI Specials/Inspection/316/2022-23 | 26/07/2022 | Flow 1 | Download | No History | View Details | N/A
43 | CP-27 | Submission of Curriculum vitae of Health & Safety Engineer & supervisor | 318. Letter for submission of Circulum vitae of Safety Engineers-Praveen & Daya | PDF | Submitted |  | KBR/BWSSB/CP-27/CV/318/2022-23 | KBR/BWSSB/CP-27/CV/318/2022-23 | 26/07/2022 | Flow 1 | Download | No History | View Details | N/A
50 | CP-27 | Inspection for DI Specials | 300.Letter for Inspection of DI Specials | PDF | Submitted |  | KBR/BWSSB/CP-27/DI Specials/Inspection/300/2022-23 | KBR/BWSSB/CP-27/DI Specials/Inspection/300/2022-23 | 21/07/2022 | Flow 1 | Download | No History | View Details | N/A
51 | CP-27 | Inspection for DI Pipes | 301.Letter for Inspection of DI pipes | PDF | Submitted |  | KBR/BWSSB/CP-27/DI pipe/Inspection/301/2022-23 | KBR/BWSSB/CP-27/DI pipe/Inspection/301/2022-23 | 21/07/2022 | Flow 1 | Download | No History | View Details | N/A
57 | CP-27 | Regarding Site issue at Hosahalli, Dismantling of front side compound wall parallel to Main Road at Hosahalli STP | 292.Letter regarding Dismantling of Compound wall | PDF | Submitted |  | KBR/BWSSB/CP-27/Hos STP/Site Issue/292/2022-23 | KBR/BWSSB/CP-27/Hos STP/Site Issue/292/2022-23 | 18/07/2022 | Flow 1 | Download | No History | View Details | N/A
62 | CP-27 | Regarding JICA Inspection | JICA Questionneries | PDF | Submitted |  | KBR/BWSSB/CP-27/JICA mission/Inspection/280/2022-2 | KBR/BWSSB/CP-27/JICA mission/Inspection/280/2022-23 | 14/07/2022 | Flow 1 | Download | No History | View Details | N/A
67 | CP-27 | DI Specials Inspection-Jindal saw Ltd | 276.Letter for Inspection of DI Specials | PDF | Submitted |  | KBR/BWSSB/CP-27/DI Specials/Inspection/276/2022-23 | KBR/BWSSB/CP-27/DI Specials/Inspection/276/2022-23 | 2022-12-07 | Flow 1 | Download | No History | View Details | N/A
68 | CP-27 | Environmental Monitoring report compliance | 270.Letter for submission of Compliance of EMP report | PDF | Submitted |  | KBR/BWSSB/CP-27/EMoP/Compliance/270/2022-23 | KBR/BWSSB/CP-27/EMoP/Compliance/270/2022-23 | 2022-11-07 | Flow 1 | Download | No History | View Details | N/A
69 | CP-27 | Setting up of Engineers office | 269.Letter for Setting up the engineers office | PDF | Submitted |  | KBR/BWSSB/CP-27/Engineers office/Setup/269/2022-23 | KBR/BWSSB/CP-27/Engineers office/Setup/269/2022-23 | 2022-11-07 | Flow 1 | Download | No History | View Details | N/A
70 | CP-27 | Right of Access | 272.Letter for Right of access | PDF | Submitted |  | KBR/BWSSB/CP-27/Right of Access/272/2022-23 | KBR/BWSSB/CP-27/Right of Access/272/2022-23 | 2022-11-07 | Flow 1 | Download | No History | View Details | N/A
71 | CP-27 | Pile Methodology-Hindustan Foundations & Constructions | 267.Letter for submission of Pile Methodology | PDF | Submitted |  | KBR/BWSSB/CP-27/Pile Methodology/267/2022-23 | KBR/BWSSB/CP-27/Pile Methodology/267/2022-23 | 2022-11-07 | Flow 1 | Download | No History | View Details | N/A
72 | CP-27 | Doddabidarakallu raising main Compliance | 268.Letter regarding DI pipes compliance Doddabidarakallu Raising main | PDF | Submitted |  | KBR/BWSSB/CP-27/DI Pipes Laying/268/2022-23 | KBR/BWSSB/CP-27/DI Pipes Laying/268/2022-23 | 2022-11-07 | Flow 1 | Download | No History | View Details | N/A
74 | CP-27 | 7th EMP report for the Month of June | EMP report | PDF | Submitted |  | KBR/BWSSB/CP-27/7th EMoP/June/264/2022-23 | KBR/BWSSB/CP-27/7th EMoP/June/264/2022-23 | 2022-09-07 | Flow 1 | Download | No History | View Details | N/A
85 | CP-27 | ROW Issues of RR Nagar | 148.Letter for submission ROW issues of RRNagara | PDF | Submitted |  | KBR/BWSSB/CP-27/148/2022-23 | KBR/BWSSB/CP-27/148/2022-23 | 28/06/2022 | Flow 1 | Download | No History | View Details | N/A
87 | CP-27 | Monthly progress report-April Month | Monthly progress report-April month-final | PDF | Submitted |  | KBR/BWSSB/CP-27/MPR-Apr/152/2022-23 | KBR/BWSSB/CP-27/MPR-Apr/152/2022-23 | 28/06/2022 | Flow 1 | Download | No History | View Details | N/A
88 | CP-27 | ROW issue of Dasarahalli zone | 149.Letter for submission of ROW issues of dasarahalli | PDF | Submitted |  | KBR/BWSSB/CP-27/149/2022-23 | KBR/BWSSB/CP-27/149/2022-23 | 28/06/2022 | Flow 1 | Download | No History | View Details | N/A
95 | CP-27 | Right of Access to sites-RR Nagar | 173.Letter regarding Right of Access to sites | PDF | Submitted |  | KBR/BWSSB/CP-27/Right of Access/173/2022-23 | KBR/BWSSB/CP-27/Right of Access/173/2022-23 | 28/06/2022 | Flow 1 | Download | No History | View Details | N/A
96 | CP-27 | DWC Pipes Compliance | 172.Letter regarding compliance of DWC pipes | PDF | Submitted |  | KBR/BWSSB/CP-27/DWC Pipes/172/2022-23 | KBR/BWSSB/CP-27/DWC Pipes/172/2022-23 | 28/06/2022 | Flow 1 | Download | No History | View Details | N/A
97 | CP-27 | Details of Fire Brigade for Dasarahalli & RR Nagar Zone | 179.Letter for submission of Details of Fire brigade for Dasarahalli & RR Nagar | PDF | Submitted |  | KBR/BWSSB/CP-27/Tie up/Fire Brigade/179/2022-23 | KBR/BWSSB/CP-27/Tie up/Fire Brigade/179/2022-23 | 28/06/2022 | Flow 1 | Download | No History | View Details | N/A
98 | CP-27 | Request for Permission for Pour of concrete at Hemigepura & Nagasandra STP | 175.LEtter for request for permission to pour concrete at Hemigepura & Nagasandra STP | PDF | Submitted |  | KBR/BWSSB/CP-27/Request for permission/175/2022-23 | KBR/BWSSB/CP-27/Request for permission/175/2022-23 | 28/06/2022 | Flow 1 | Download | No History | View Details | N/A
103 | CP-27 | Submission of DD for Executive Engineer Elec., KTPCL | DD | PDF | Submitted |  | KBR/BWSSB/CP-27/DD/225/2022-23 | KBR/BWSSB/CP-27/DD/225/2022-23 | 27/06/2022 | Flow 1 | Download | No History | View Details | N/A
104 | CP-27 | curriculum vitae Submission of QA/QC Engineer | Documents.... | PDF | Submitted |  | KBR/BWSSB/CP-27/CV/211/2022-23 | KBR/BWSSB/CP-27/CV/211/2022-23 | 27/06/2022 | Flow 1 | Download | No History | View Details | N/A
105 | CP-27 | Right of Way issue RR Nagar Zone | 229.Letter for ROW issues RR Nagar zone | PDF | Submitted |  | KBR/BWSSB/CP-27/ RR Nagar zone/ROW/229/2022-23 | KBR/BWSSB/CP-27/ RR Nagar zone/ROW/229/2022-23 | 27/06/2022 | Flow 1 | Download | No History | View Details | N/A
106 | CP-27 | Regarding Additional information-PCB | 230.Letter regarding additional information-PCB | PDF | Submitted |  | KBR/BWSSB/CP-27/13MLD/PCB-CFE/230/2022-23 | KBR/BWSSB/CP-27/13MLD/PCB-CFE/230/2022-23 | 27/06/2022 | Flow 1 | Download | No History | View Details | N/A
107 | CP-27 | GPR survey drawings of Dasarahalli zone | GPR survey drawings of Dasarahalli zone | PDF | Submitted |  | KBR/BWSSB/CP-27/Trenchless works/193/2022-23 | KBR/BWSSB/CP-27/Trenchless works/193/2022-23 | 27/06/2022 | Flow 1 | Download | No History | View Details | N/A
108 | CP-27 | Environmental Monitoring report for the Month of May 2022 | 6th EMoP report for the Month of May 2022 | PDF | Submitted |  | KBR/BWSSB/CP-27/6th EMoP/May/184/2022-23 | KBR/BWSSB/CP-27/6th EMoP/May/184/2022-23 | 27/06/2022 | Flow 1 | Download | No History | View Details | N/A
109 | CP-27 | Right of Way issue | 219.Letter regarding right of way issue | PDF | Submitted |  | Right of Way issue | KBR/BWSSB/CP-27/ROW Issues/219/2022-23 | 27/06/2022 | Flow 1 | Download | No History | View Details | N/A
110 | CP-27 | Right of Way issue Dasarahalli Zone | 228.Letter for ROW issues Dasarahalli zone | PDF | Submitted |  | KBR/BWSSB/CP-27/Dasarahalli zone/ROW/228/2022-23 | KBR/BWSSB/CP-27/Dasarahalli zone/ROW/228/2022-23 | 27/06/2022 | Flow 1 | Download | No History | View Details | N/A
116 | CP-27 | Topographical & GPR survey drawings of RR Nagar | GPR Survey Topographical survey drawings-RR Nagar | PDF | Submitted |  | KBR/BWSSB/CP-27/Trenchless works/198/2022-23 | KBR/BWSSB/CP-27/Trenchless works/198/2022-23 | 27/06/2022 | Flow 1 | Download | No History | View Details | N/A
-11 | CP-27 | curriculum vitae Submission of QA/QC | Documents.... | PDF | Submitted |  | KBR/BWSSB/CP-27/CV/211/2022-23 | KBR/BWSSB/CP-27/CV/211/2022-23 | 20/06/2022 | Flow 1 | Download | No History | View Details | N/A